# Post-Session Assessment: Scenario-Based Hands-On Activity Duration: 30 minutes

Assessment Overview

Objective: Demonstrate practical application of GenAI skills learned during the session by solving a realistic health plan project management challenge.

Format: Individual work with optional pair validation (last 5 minutes)

# Tools Needed:

- Laptop/tablet with internet access

- Access to ChatGPT, Claude, or Gemini

- Scenario handout (provided below)

# Assessment Instructions (5 minutes) Participant Instructions:

You will receive a realistic health plan PM scenario containing multiple challenges. Your task is to:

# Read the scenario carefully (5 min)

- Create and execute AI prompts to address the challenges (20 min)

- Document your outputs (throughout)

- Quick peer validation (optional, last 5 min)

# What You'll Submit:

- The prompts you created (copy-paste into assessment document)

- The AI outputs you received (screenshots or copy-paste)

- Your validation notes (how you would verify/improve the AI output)

- Brief reflection on responsible AI considerations

# Scenario: The Digital Member Portal Crisis Background Context:

You are the Project Manager for Project HealthConnect, a major initiative to launch Elevance Health's new member self-service portal. This portal will allow 2.3 million members across three states (Indiana, Ohio, Kentucky) to:

  - View and download their insurance cards

  - Check claims status in real-time

  - Find in-network providers

  - Schedule preventive care appointments

  - Access their medication list and pharmacy benefits

The executive team has positioned this as a flagship digital transformation initiative aligned with Elevance Health's consumer-centered approach.

# Current Situation (Today: February 3, 2026):

Slack Message from Tech Lead received 20 minutes ago:

@ProjectManager - URGENT

We have a major problem. Our security team just ffagged a critical vulnerability in the authentication module during final UAT. We need to apply a patch that will require:

- 5 days of additional development work - Complete regression testing (estimated 1 week) - Re-certification from InfoSec (3-5 days)

This pushes us past our Feb 28 launch date. BUT - Marketing already sent a press release to media outlets announcing the Feb 28 launch, and we've sent 500K+ emails to members saying "Coming February 28!"

Also, our vendor (AuthSecure) is telling us they can't provide the patch until Feb 10 because their team is at a conference. Our compliance officer is asking if we should report this to state insurance commissioners as a potential data security issue.

What do we do?

- Marcus (Tech Lead)

# Additional Information You Have:

Current Project Status:

  - Budget: $4.2M spent of $4.5M allocated (93% consumed)

  - Timeline: Launch date Feb 28, 2026 (25 days away)

  - Team: 8 internal developers, 3 vendor consultants, 2 UX designers, 1 compliance specialist

  - Member Impact: 2.3M members expecting portal access

  - Executive Sponsor: Chief Digital Information Officer (very visible initiative)

# Key Stakeholders:

  - Executive Leadership: Expecting this to demonstrate digital capabilities

  - Marketing/Communications: Already committed to Feb 28 in public messaging

  - Compliance s Legal: Concerned about security vulnerability and regulatory reporting

  - Member Services: Getting calls from members asking when portal goes live

  - IT Security: Will not approve launch without vulnerability fix

  - State Regulators: Indiana, Ohio, Kentucky insurance departments (must be notified of security issues)

  - Members: 2.3M people expecting improved digital experience

# Recent Context:

  - This project was announced at last quarter's investor earnings call

  - Competitor BCBS just launched their portal last month (pressure to keep pace)

  - Member satisfaction scores have declined 8% in recent surveys

  - Executive team views this as critical to Elevance's "digitally enabled healthcare" strategy

# Your Assessment Tasks (Complete ALL 4 Tasks)

TASK 1: Executive Stakeholder Communication (10 minutes)

Challenge: You need to brief the Chief Digital Information Officer (CDIO) on this situation within the next 2 hours via email.

# Your Actions:

- Craft a prompt for GenAI to help you create an executive brief that:

  - Clearly explains the situation and its implications

  - Presents 2-3 realistic options with trade-offs (consider: delay launch, phased rollout, enhanced monitoring, etc.)

  - Provides a recommendation with rationale

  - Addresses reputational, member experience, and compliance risks

  - Maintains appropriate tone for C-suite audience

  - Keeps it concise (executives are busy)

- Generate the output using your chosen AI tool

- Validation Check: Identify at least 2 specific pieces of information you would need to add or verify before sending this to the CDIO

# Document:

- Your prompt

- AI output (or screenshot)

- Your validation notes

# TASK 2: Risk Assessment s Crisis Response Plan (8 minutes)

Challenge: Create a focused risk assessment and immediate action plan for the next 72 hours.

# Your Actions:

- Create a prompt to generate:

  - Top 5 risks in this situation (member trust, regulatory, reputational, financial, operational)

  - Impact and likelihood assessment for each

  - Immediate mitigation actions (next 24-72 hours)

  - Risk owners by role

  - Escalation triggers ("If X happens, then we must...")

- Generate the output

- HIPAA/Compliance Check: Note any compliance or security considerations the AI might have missed that are specific to health plan member data

# Document:

- Your prompt

- AI output

- Compliance gaps you identified

# TASK 3: Multi-Stakeholder Communication Strategy (7 minutes)

Challenge: You need different messages for different audiences. Some stakeholders need to know NOW, others can wait.

# Your Actions:

- Create prompts to draft TWO different communications:

Communication A: Internal Slack message to the project team (developers, UX, vendor)

  - Acknowledge the situation

  - Outline immediate next steps

  - Set expectations for timeline decisions

  - Maintain team morale

  - Keep it brief and actionable

Communication B: Draft talking points for Marketing/Communications team

  - Help them prepare member-facing messaging

  - Address what to say if members call asking about Feb 28 launch

  - Balance transparency with not creating panic

  - Align with Elevance Health's consumer-centered values

  - Cannot contain PHI or specific member information

- Generate both outputs

- Brand s Sensitivity Check: Identify any language or tone issues that might not align with Elevance Health's brand values or could damage member trust

# Document:

- Both prompts

- Both outputs

- Your brand/sensitivity concerns

# TASK 4: Decision Framework s Resource Planning (5 minutes)

Challenge: Leadership will ask "What do you need to fix this?" You need to think through resource implications.

# Your Actions:

- Create a prompt to help you:

  - Map out resource needs for each potential option (delay, phased launch, etc.)

  - Identify if you need additional budget, people, or vendor support

  - Highlight dependencies (what must happen before what)

  - Create a decision matrix comparing options

- Generate the output

- Reality Check: Note what specific information you're missing that the AI cannot provide (e.g., actual vendor availability, specific team member capacity, real budget constraints)

# Document:

- Your prompt

- AI output

- Information gaps you identified

# Submission Format

Complete the Assessment Document: PARTICIPANT NAME: 		 DATE:

AI TOOL USED:

═══════════════════════════════════════

TASK 1: EXECUTIVE STAKEHOLDER COMMUNICATION

═══════════════════════════════════════

MY PROMPT:

[Paste here]

AI OUTPUT:

[Paste here]

VALIDATION NOTES - Information I need to verify/add: 1.

2.

═══════════════════════════════════════

TASK 2: RISK ASSESSMENT C CRISIS RESPONSE

═══════════════════════════════════════

MY PROMPT:

[Paste here]

AI OUTPUT:

[Paste here]

COMPLIANCE GAPS IDENTIFIED:

1.

2.

═══════════════════════════════════════

TASK 3: MULTI-STAKEHOLDER COMMUNICATION

═══════════════════════════════════════

PROMPT A (Project Team Slack Message):

[Paste here]

OUTPUT A:

[Paste here]

PROMPT B (Marketing Talking Points):

[Paste here]

OUTPUT B:

[Paste here]

BRAND/SENSITIVITY CONCERNS:

1.

2.

═══════════════════════════════════════

TASK 4: DECISION FRAMEWORK C RESOURCE PLANNING

═══════════════════════════════════════

MY PROMPT:

[Paste here]

AI OUTPUT:

[Paste here]

INFORMATION GAPS (What AI cannot know): 1.

2.

3.

═══════════════════════════════════════

FINAL REFLECTION (2-3 sentences each)

═══════════════════════════════════════

What was the most valuable GenAI application you discovered during this exercise?

What responsible AI consideration would you prioritize in this scenario?

If you were actually in this situation, what would you do FIRST and why?